## 📊 Summary Dashboard
WalaPlus Platform — Testing & Adoption Tracker v4.0
25-Day Testing & Adoption Plan ¦ Team: Sarah Hijazi & Mohammed Al Muzini ¦ Enhanced for Replit deployment testing
LIVE METRICS — auto-calculated from the tracker sheets
| Test Completion | Issue Coverage | Team Adoption | Scenarios
| Target: 100% by Day 25 | Target: >= 80% | Target: >= 50% | Target: 100 scenarios
WHAT'S NEW IN v4.0
✓ Testing Tracker expanded from 61 → 120 tests (auth, security, API, PDPL, webhooks)
✓ Expected Issues expanded from 49 → 75 failure modes (security, auth bypass, injection, webhook)
✓ Scenarios expanded from 93 → 100 real-world tasks (security verification, PDPL, cross-module)
✓ Added Priority column (P0-Critical, P1-High, P2-Medium) to Testing Tracker and Expected Issues
✓ Added Test URL / API Endpoint column with exact Replit URLs for every test
✓ Added Expected Result column describing what success looks like
✓ Added Related Test # column in Expected Issues for traceability
✓ All v3.6 code fixes reflected (22 security hardening fixes)
✓ Adoption Tracker expanded with Auth, Feedback, Onboarding, Guide areas
HOW TO USE THIS WORKBOOK
🧪 Sheet 2 — Testing Tracker: Go through each row. Use Priority to focus on P0 first, then P1. Change Status to: Not started / In progress / Blocked / Done / Fail
🔍 Sheet 3 — Expected Issues: After testing, mark Y or N — this shows which failure modes your tests can catch
👥 Sheet 4 — Adoption Tracker: Each person marks Y / N / P for areas they use regularly
🎯 Sheet 5 — Scenarios: Work through 4-5 per day. Follow the 'How to Do It' steps. Mark Done when complete.
📊 This Summary Dashboard updates automatically as you fill in the other sheets.

## 🧪 Testing Tracker
Test Completion % →
🧪 Testing Tracker — 120 tests · Enhanced for Replit v4.0 · Security + API + Auth coverage
Priority: P0=Critical (must pass) · P1=High (should pass) · P2=Medium (nice to pass) ¦ Status: Not started / In progress / Blocked / Done / Done (code fix) / Fail
Seq | # | Priority | Area (Screen Name) | What We Are Checking | Test URL / API Endpoint | Expected Result | Do This After | Phase (Day) | Suggested Owner | Responsible Person | Status | Notes
1 | 1 | P0-Critical | Auth — Login Page | Login page loads and Replit OIDC redirect works | https://qms-dashboard.replit.app/login | Login page renders; 'Log in with Replit' button redirects to Replit OIDC | — | 1 | Admin |  | Not started
2 | 2 | P0-Critical | Auth — OIDC Callback | OIDC callback creates session and redirects to dashboard | https://qms-dashboard.replit.app/api/callback | After Replit auth, redirected to / with walaplus_session cookie set | Step 1 | 1 | Admin |  | Not started
3 | 3 | P0-Critical | Auth — Admin Key Login | Admin can login via API key on login page | https://qms-dashboard.replit.app/api/admin/auth | POST with valid ADMIN_API_KEY sets admin_key cookie; redirects to / | Step 1 | 1 | Admin |  | Not started
4 | 4 | P0-Critical | Auth — Logout | POST-only logout clears session | POST https://qms-dashboard.replit.app/api/logout | Session cookie cleared; redirected to /login | Step 2 | 1 | Admin |  | Not started
5 | 5 | P0-Critical | Auth — Session Validation | Protected pages redirect to /login if unauthenticated | https://qms-dashboard.replit.app/qms (no cookie) | 302 redirect to /login | Step 2 | 1 | Admin |  | Not started
6 | 6 | P0-Critical | Integrations — CRM Leads | CRM connection works; Leads data flows in | https://qms-dashboard.replit.app/crm (Leads tab) | Leads list loads with real CRM data | Step 3 | 1 | Quality / Admin | Sarah Hijazi | Blocked | Configure ZOHO_CLIENT_ID, ZOHO_CLIENT_SECRET, ZOHO_REFRESH_TOKEN
7 | 7 | P0-Critical | Integrations — CRM Deals | CRM connection works; Deals data flows in | https://qms-dashboard.replit.app/crm (Deals tab) | Deals list loads with real CRM data | Step 6 | 1 | Quality / Admin | Sarah Hijazi | Blocked | Configure Zoho secrets first
8 | 8 | P1-High | Integrations — CRM Contacts | Contacts module accessible via CRM page | https://qms-dashboard.replit.app/crm (Contacts tab) | Contacts list loads | Step 6 | 1 | Quality / Admin |  | Not started
9 | 9 | P1-High | Integrations — CRM Tasks | Tasks module accessible via CRM page | https://qms-dashboard.replit.app/crm (Tasks tab) | Tasks list loads | Step 6 | 1 | Quality / Admin |  | Not started
10 | 10 | P1-High | Integrations — Status Overview | Integration status panel shows connection health | GET https://qms-dashboard.replit.app/api/integrations/status | JSON with zoho/google/email status objects | Steps 6-7 | 1 | Quality / Admin | Sarah Hijazi | Blocked
11 | 11 | P1-High | API — Health Check | Health endpoint responds | GET https://qms-dashboard.replit.app/api/health | 200 OK with health status JSON | — | 1 | Admin |  | Not started | Public endpoint, no auth required
12 | 12 | P1-High | API — Smoke Test | Smoke test endpoint responds | GET https://qms-dashboard.replit.app/api/smoke | 200 OK with component status checks | — | 1 | Admin |  | Not started | Public endpoint, no auth required
13 | 13 | P0-Critical | Admin Panel — Access | Admin panel loads with API key | https://qms-dashboard.replit.app/admin | Admin panel renders after admin_key cookie is set | Step 3 | 2 | Admin | Sarah Hijazi | Not started | Requires ADMIN_API_KEY
14 | 14 | P0-Critical | Admin Panel — Governance Documents | Upload/view governance documents for AI audit rules | https://qms-dashboard.replit.app/admin (Documents tab) | Document list loads; can upload new document | Step 13 | 2 | Admin | Sarah Hijazi | Not started
15 | 15 | P0-Critical | Admin Panel — Scorecards | Upload/view scorecards for SDR/Sales agents | https://qms-dashboard.replit.app/admin (Scorecards tab) | Scorecard list loads; can create new scorecard | Step 14 | 2 | Admin | Sarah Hijazi | Not started
16 | 16 | P1-High | Admin Panel — Activity Log | View log of admin activities | https://qms-dashboard.replit.app/admin (Activity tab) | Activity entries appear after platform actions | Step 15 | 2 | Admin | Sarah Hijazi | Not started | Empty initially — populates after use
17 | 17 | P1-High | Admin Panel — Audit Runs List | View list of quality audit runs | https://qms-dashboard.replit.app/admin (Audit Runs tab) | Audit run entries appear after running AI audit | Step 15 | 2 | Admin | Sarah Hijazi | Not started
18 | 18 | P1-High | Admin Panel — Automated Triggers | View automated trigger schedule | https://qms-dashboard.replit.app/admin (Triggers tab) | Trigger list with AUDIT_COMPLETED, NC_DETECTED, CAPA_REQUIRED | Steps 15-17 | 2 | Admin | Sarah Hijazi | Not started | Auto-created when audits run
19 | 19 | P0-Critical | Quality Audit — Full Run | Run AI audit end-to-end; results for Leads + Deals | POST https://qms-dashboard.replit.app/api/audit/trigger | Audit completes; scores saved; triggers fire; email sent | Steps 14-15 | 3 | Quality | Sarah Hijazi | Not started | Requires Zoho + OpenAI keys
20 | 20 | P0-Critical | Quality Audit — Fallback Mode | Audit runs even without Inngest dev server | POST https://qms-dashboard.replit.app/api/audit/trigger | directAuditRunner executes if Inngest fails; same results | Step 19 | 3 | Quality |  | Not started | Inngest-first with direct fallback
21 | 21 | P1-High | Quality Audit — Email Report | Email report sent after audit | Check configured email inbox | Email with quality scores + recommendations arrives | Step 19 | 3 | Quality |  | Not started | Requires RESEND_API_KEY
22 | 22 | P1-High | Quality Audit — Trigger Chain | All 3 triggers fire after audit | GET https://qms-dashboard.replit.app/api/qms/triggers | AUDIT_COMPLETED always; NC_DETECTED if issues>0; CAPA_REQUIRED if critical | Step 19 | 3 | Quality |  | Not started
23 | 23 | P0-Critical | Quality Dashboard — Main Page | Main page shows quality score + breakdown | https://qms-dashboard.replit.app/ | Overall score, People/Process/Governance breakdown, audit summary | Step 19 | 4 | Quality |  | Not started
24 | 24 | P1-High | Quality Dashboard — Latest Audit Result | Latest audit result visible | https://qms-dashboard.replit.app/ (Latest Result section) | Shows most recent audit date, scores, issues count | Step 19 | 4 | Quality |  | Not started
25 | 25 | P1-High | Quality Dashboard — Audit History | Audit history timeline visible | https://qms-dashboard.replit.app/ (History section) | List of past audit runs with dates and scores | Step 19 | 4 | Quality |  | Not started
26 | 26 | P2-Medium | Quality Dashboard — AI Agent Performance | AI agent performance metrics | https://qms-dashboard.replit.app/ (Agent section) | SDR + Sales agent performance shown | Step 19 | 4 | Quality |  | Not started | Requires OpenAI key
27 | 27 | P1-High | Quality Dashboard — Run AI Audit Button | Purple button triggers audit from dashboard | https://qms-dashboard.replit.app/ (click button) | Button shows spinner, then 'Audit Started!'; dashboard refreshes | Steps 14-15 | 4 | Quality |  | Not started | FIXED: Inngest fallback added
28 | 28 | P1-High | Quality Dashboard — Export PDF | PDF export of dashboard | https://qms-dashboard.replit.app/ (Export button) | PDF file downloads with quality scores | Step 19 | 4 | Quality |  | Not started
29 | 29 | P0-Critical | QMS Dashboard — Main Page | QMS overview with summary cards | https://qms-dashboard.replit.app/qms | Evaluations, Open CAPA, Open NC, Training Completion, Audit Runs cards | Step 19 | 5 | Quality |  | Done (code fix) | Audit Runs card added
30 | 30 | P1-High | QMS Dashboard — CAPA List | CAPA tab shows corrective/preventive actions | https://qms-dashboard.replit.app/qms (CAPA tab) | CAPA list loads; can create new CAPA | Step 29 | 5 | Quality |  | Not started
31 | 31 | P1-High | QMS Dashboard — CAPA Create | Can create a new CAPA record | POST https://qms-dashboard.replit.app/api/qms/capa | CAPA created with title, type, root cause, assigned_to | Step 30 | 5 | Quality |  | Not started
32 | 32 | P0-Critical | QMS Dashboard — Nonconformances | NC tab with New NC button works | https://qms-dashboard.replit.app/qms (NC tab) | NC list loads; New NC button opens modal | Step 29 | 5 | Quality |  | Done (code fix) | New NC button + modal added
33 | 33 | P1-High | QMS Dashboard — Create NC | Can create NC with all fields | POST https://qms-dashboard.replit.app/api/qms/nc | NC created with title, type, severity, source, assigned_to | Step 32 | 5 | Quality |  | Not started | Types: process/product/system/documentation/data_quality
34 | 34 | P1-High | QMS Dashboard — Deal Evaluations | Deal evaluations tab works | https://qms-dashboard.replit.app/qms (Deal Evaluations tab) | Evaluation list loads; can run evaluations | Step 29 | 5 | Quality |  | Not started | Requires CRM deals data
35 | 35 | P2-Medium | QMS Dashboard — Training | Training tab with courses/assignments | https://qms-dashboard.replit.app/qms (Training tab) | Course list and assignments visible | Step 29 | 5 | Quality |  | Not started
36 | 36 | P2-Medium | QMS Dashboard — Framework Config | Evaluation framework configuration | https://qms-dashboard.replit.app/qms (Framework tab) | Framework dimensions, criteria, weights editable | Step 29 | 5 | Quality |  | Not started
37 | 37 | P1-High | QMS Dashboard — Trigger Actions | Trigger acknowledge/dismiss/decide | https://qms-dashboard.replit.app/qms (Triggers tab) | Can acknowledge, dismiss, or decide on each trigger | Step 22 | 5 | Quality |  | Not started
38 | 38 | P0-Critical | GRC Control Tower — Main Page | GRC overview with all summary cards | https://qms-dashboard.replit.app/grc | Risks, Policies, Compliance, Findings, Vendors, Controls cards + heat map | — | 6 | GRC | Mohammed AlMuzaini | Done (code fix) | Audit Readiness table added
39 | 39 | P1-High | GRC Control Tower — Period Filter | Period filter (MTD/QTD/YTD) works | https://qms-dashboard.replit.app/grc (filter) | Data changes when switching periods | Step 38 | 6 | GRC |  | Not started
40 | 40 | P1-High | GRC Control Tower — Handoff Rules Display | Handoff rules visible on GRC page | https://qms-dashboard.replit.app/grc (Handoff section) | List of quality-to-GRC handoff rules with triggers | Step 38 | 6 | GRC |  | Not started
41 | 41 | P1-High | Risk Register — Risk List | View list of enterprise risks | https://qms-dashboard.replit.app/risks | Risk list with likelihood, impact, score, owner, status | Step 38 | 7 | GRC | Mohammed AlMuzaini | Done
42 | 42 | P1-High | Risk Register — Create Risk | Can create a new risk | POST https://qms-dashboard.replit.app/api/risks | Risk created with UUID public_id; appears in list | Step 41 | 7 | GRC |  | Not started
43 | 43 | P1-High | Risk Register — Heat Map | Risk heat map displays correctly | https://qms-dashboard.replit.app/risks (Heat Map) | 4x4 grid with risks plotted by likelihood x impact | Step 41 | 7 | GRC | Mohammed AlMuzaini | Done
44 | 44 | P1-High | Risk Register — Treatment Actions | Risk treatment actions CRUD | PUT https://qms-dashboard.replit.app/api/risks/treatment/:actionId | Treatment action updated by UUID (not numeric ID) | Step 42 | 7 | GRC |  | Not started | FIXED: UUID resolution corrected
45 | 45 | P1-High | Risk Register — CSV Export | Export risks to CSV | https://qms-dashboard.replit.app/risks (Export button) | CSV file downloads with all risk data | Step 41 | 7 | GRC |  | Not started
46 | 46 | P1-High | Policy Governance — Policy List | View list of policies | https://qms-dashboard.replit.app/policies | Policy list loads with status, category, owner | Step 38 | 8 | GRC | Mohammed AlMuzaini | Done (code fix) | JS SyntaxError fixed
47 | 47 | P1-High | Policy Governance — Create Policy | Create a new policy | https://qms-dashboard.replit.app/policies (New Policy) | Policy created in Draft status with all fields | Step 46 | 8 | GRC |  | Not started
48 | 48 | P1-High | Policy Governance — Lifecycle Workflow | Draft→Review→Approval→Published→Archived | https://qms-dashboard.replit.app/policies (lifecycle buttons) | Each transition works; GRC approval required before publish | Step 47 | 8 | GRC |  | Not started
49 | 49 | P1-High | Policy Governance — GRC Approval | Request GRC Approval button works | POST https://qms-dashboard.replit.app/api/policies/:id/grc-approval | Policy moves to Approved status; ready for publishing | Step 48 | 8 | GRC |  | Not started | FIXED: Template literal syntax corrected
50 | 50 | P1-High | Compliance Tracker — Regulations | View regulations list | https://qms-dashboard.replit.app/compliance | Regulation list with jurisdiction, effective dates | Step 38 | 8 | GRC | Mohammed AlMuzaini | Done
51 | 51 | P1-High | Compliance Tracker — Obligations | View obligations list | https://qms-dashboard.replit.app/compliance (Obligations) | Obligation list with due dates, priority, status | Step 50 | 8 | GRC | Mohammed AlMuzaini | Done
52 | 52 | P1-High | Compliance Tracker — Summary | Compliance summary/score | GET https://qms-dashboard.replit.app/api/compliance/summary | Overall compliance score and per-framework breakdown | Step 50 | 8 | GRC | Mohammed AlMuzaini | Done
53 | 53 | P1-High | Audit Readiness — Audit List | View audit list | https://qms-dashboard.replit.app/audits | Audit list with code, type, status, lead, findings count | Step 38 | 9 | GRC | Mohammed AlMuzaini | Not started
54 | 54 | P1-High | Audit Readiness — Findings | View audit findings | https://qms-dashboard.replit.app/audits (Findings) | Finding list with severity, status, remediation | Step 53 | 9 | GRC | Mohammed AlMuzaini | Not started
55 | 55 | P2-Medium | Audit Readiness — Evidence Packs | Evidence pack compilation | GET https://qms-dashboard.replit.app/api/audits/evidence | Evidence packs with status tracking | Step 53 | 9 | GRC |  | Not started
56 | 56 | P1-High | Vendor Risk — Vendor List | View vendor list | https://qms-dashboard.replit.app/vendors | Vendor list with risk scoring | Step 38 | 9 | GRC | Mohammed AlMuzaini | Done
57 | 57 | P1-High | Vendor Risk — Vendor Summary | Vendor risk summary view | https://qms-dashboard.replit.app/vendors (Summary) | High/Medium/Low/Critical vendor breakdown | Step 56 | 9 | GRC | Mohammed AlMuzaini | Done
58 | 58 | P1-High | PDPL — Compliance Status | PDPL compliance status loads | https://qms-dashboard.replit.app/pdpl | PDPL status page with compliance indicators | — | 10 | GRC / GRQ | Mohammed AlMuzaini | Not started | FIXED: Nav init added
59 | 59 | P1-High | PDPL — Data Inventory | View/create data inventory entries | GET https://qms-dashboard.replit.app/api/pdpl/inventory | Data inventory list; can add new entries | Step 58 | 10 | GRC / GRQ |  | Not started | Requires auth (requireAuthOrKey)
60 | 60 | P1-High | PDPL — DSAR Requests | Submit/view DSAR requests | POST https://qms-dashboard.replit.app/api/pdpl/dsar | DSAR created; appears in list with status tracking | Step 58 | 10 | GRC / GRQ |  | Not started | Requires write role (requireWriteRole)
61 | 61 | P1-High | PDPL — Data Incidents | Log/view data incidents | POST https://qms-dashboard.replit.app/api/pdpl/incidents | Incident logged with severity and response tracking | Step 58 | 10 | GRC / GRQ |  | Not started | Requires write role
62 | 62 | P2-Medium | PDPL — AI Guardrails | AI guardrail patterns active | GET https://qms-dashboard.replit.app/api/pdpl/guardrails | PII masking patterns returned | Step 58 | 10 | GRC / GRQ |  | Not started
63 | 63 | P1-High | Call Intelligence — Call Records | View call records | https://qms-dashboard.replit.app/calls | Call records list with metadata | — | 11 | Quality |  | Not started | Requires Five9/Twilio call data ingestion
64 | 64 | P1-High | Call Intelligence — Upload | Upload call recording | POST https://qms-dashboard.replit.app/api/calls/upload | Call uploaded and queued for analysis | Step 63 | 11 | Quality |  | Not started | Requires auth (session or admin)
65 | 65 | P1-High | Call Intelligence — Analytics | Call analytics/trends | https://qms-dashboard.replit.app/calls (Analytics) | QA scores, sentiment, trends visible | Step 63 | 11 | Quality |  | Done
66 | 66 | P1-High | ROI Evaluation — Initiatives | View ROI initiatives | https://qms-dashboard.replit.app/roi | Initiative list with business case data | — | 11 | Quality |  | Not started
67 | 67 | P1-High | ROI Evaluation — Create Initiative | Create new ROI initiative | POST https://qms-dashboard.replit.app/api/roi/initiatives | Initiative created with costs, benefits, NPV | Step 66 | 11 | Quality |  | Not started
68 | 68 | P2-Medium | ROI Evaluation — Analytics | ROI analytics/trends | https://qms-dashboard.replit.app/roi (Analytics) | ROI trend data and comparisons | Step 66 | 11 | Quality |  | Not started
69 | 69 | P1-High | Team Performance — Members | View team members list | https://qms-dashboard.replit.app/team | Team member list with departments/roles | — | 12 | Quality |  | Done (code fix) | FIXED: Add Member button added
70 | 70 | P1-High | Team Performance — Add Member | Add a new team member | https://qms-dashboard.replit.app/team (Add Member button) | Member created with name, email, role, department | Step 69 | 12 | Quality |  | Not started
71 | 71 | P1-High | Team Performance — Performance Data | View performance metrics | https://qms-dashboard.replit.app/team (Overview tab) | Performance scores, training compliance visible | Step 69 | 12 | Quality |  | Not started
72 | 72 | P2-Medium | Team Performance — Training Matrix | Training matrix and gap analysis | https://qms-dashboard.replit.app/team (Training Matrix tab) | Skill gaps identified per team member | Step 69 | 12 | Quality |  | Not started
73 | 73 | P1-High | Project Portfolio — Projects | View project list | https://qms-dashboard.replit.app/projects | Project list with status, milestones | — | 12 | Quality / GRQ | Mohammed AlMuzaini | Done
74 | 74 | P1-High | Data Migration — Import | Data import functionality | https://qms-dashboard.replit.app/migration | Import templates downloadable; import jobs trackable | — | 13 | GRQ / GRC | Sarah Hijazi | Not started
75 | 75 | P2-Medium | Data Migration — Dedup Rules | Deduplication rules for imports | https://qms-dashboard.replit.app/migration (Dedup) | Dedup rules visible and configurable | Step 74 | 13 | GRQ / GRC |  | Not started
76 | 76 | P1-High | System Event Logs — List | View event log entries | https://qms-dashboard.replit.app/logs | Log entries with action, user, timestamp, filterable | — | 13 | All | Mohammed AlMuzaini | Not started | Empty initially — populates with use
77 | 77 | P2-Medium | System Event Logs — Filtering | Filter logs by action/user/date | https://qms-dashboard.replit.app/logs (filters) | Filtered results match criteria | Step 76 | 13 | All |  | Not started
78 | 78 | P2-Medium | Table F Engine — Config | Table F configuration view | https://qms-dashboard.replit.app/tablef | Governance rules visible for CRM classification | Steps 14-15 | 14 | Quality / Admin |  | Not started | Needs governance documents uploaded first
79 | 79 | P2-Medium | Table F Engine — Processing | Table F processes data correctly | https://qms-dashboard.replit.app/tablef (Results) | Records classified per governance rules | Step 78 | 14 | Quality / Admin |  | Not started
80 | 80 | P2-Medium | Sandbox — Access | Sandbox environment accessible | https://qms-dashboard.replit.app/sandbox | Sandbox page loads with mock data options | — | 14 | Quality / Admin |  | Not started
81 | 81 | P2-Medium | Sandbox — Mock Data | Generate and view mock data | GET https://qms-dashboard.replit.app/api/sandbox/leads | Mock leads/deals returned (not real CRM data) | Step 80 | 14 | Quality / Admin |  | Not started
82 | 82 | P1-High | Users & Access — User List | View user list (admin only) | GET https://qms-dashboard.replit.app/api/rbac/users | User list with roles and status | Step 3 | 14 | Admin | Sarah Hijazi | Not started | Requires requireAdminOrKey
83 | 83 | P1-High | Users & Access — Role Change | Change a user's role | PUT https://qms-dashboard.replit.app/api/rbac/users/:id | User role updated; permissions change immediately | Step 82 | 14 | Admin |  | Not started
84 | 84 | P1-High | Scorecard — View | View employee scorecards | https://qms-dashboard.replit.app/scorecard | Scorecard with KPI snapshots per employee | Step 19 | 15 | Quality | Sarah Hijazi | Not started
85 | 85 | P1-High | Duplicate Radar — Summary | View duplicate detection summary | https://qms-dashboard.replit.app/duplicates | Duplicate cluster counts for Leads/Contacts/Deals | Steps 6-7 | 15 | Quality | Sarah Hijazi | Done
86 | 86 | P2-Medium | Duplicate Radar — Scan | Trigger Zoho duplicate scan | POST https://qms-dashboard.replit.app/api/duplicates/scan-zoho | Scan runs; new clusters detected | Step 85 | 15 | Quality |  | Not started | Requires requireAdminOrKey
87 | 87 | P1-High | Handoff — Rules | View/create handoff rules | GET https://qms-dashboard.replit.app/api/handoff/rules | Handoff rule list with source/target/triggers | Steps 19, 38 | 15 | Quality / GRC |  | Not started | Empty until configured
88 | 88 | P2-Medium | Handoff — Events | View handoff event log | GET https://qms-dashboard.replit.app/api/handoff/events | Event list with timestamps and status | Step 87 | 15 | Quality / GRC |  | Not started
89 | 89 | P1-High | KPI Tracking — KPI List | View KPI definitions | https://qms-dashboard.replit.app/kpis | KPI list with targets and current values | — | 15 | GRQ / Quality |  | Done
90 | 90 | P1-High | KPI Tracking — Summary | KPI summary vs targets | https://qms-dashboard.replit.app/kpis (Summary) | Visual indicators for on-track/at-risk KPIs | Step 89 | 15 | GRQ / Quality |  | Done
91 | 91 | P0-Critical | Executive Dashboard — Main View | Executive dashboard loads with cross-module data | https://qms-dashboard.replit.app/executive | Quality, Risk, Compliance, KPI summaries all present | Steps 19, 38 | 16 | Quality / GRC / GRQ |  | Done (code fix) | FIXED: API response parsing corrected
92 | 92 | P1-High | Executive Dashboard — Risk Data | Top risks display correctly | https://qms-dashboard.replit.app/executive (Risks section) | Risk list from /api/risks parsed correctly (data.risks array) | Step 91 | 16 | Quality / GRC |  | Not started | FIXED: Response parsing for {{risks,total}} object
93 | 93 | P1-High | Executive Dashboard — Compliance Data | Compliance data from correct endpoint | https://qms-dashboard.replit.app/executive (Compliance section) | Compliance data from /api/compliance/summary (not /frameworks) | Step 91 | 16 | Quality / GRC |  | Not started | FIXED: Endpoint changed from /frameworks to /summary
94 | 94 | P1-High | Executive Dashboard — Data Accuracy | Numbers match individual module screens | https://qms-dashboard.replit.app/executive vs individual pages | Cross-reference risk count, compliance score with /risks and /compliance | Step 91 | 16 | Quality / GRC / GRQ |  | Not started
95 | 95 | P0-Critical | Security — Rate Limiting | Rate limiter blocks excessive requests | GET https://qms-dashboard.replit.app/api/dashboard (11+ times in 60s unauthenticated) | 429 Too Many Requests after 10 unauthenticated reads | — | 17 | Admin |  | Not started | Tiered: 10 unauth read / 3 unauth write / 100 auth read
96 | 96 | P0-Critical | Security — Auth Endpoints Rate Limit | Auth endpoints limited to 5/min | POST https://qms-dashboard.replit.app/api/login (6+ times) | 429 after 5 attempts on auth endpoints | — | 17 | Admin |  | Not started
97 | 97 | P0-Critical | Security — Unauthenticated API Access | Protected APIs return 401 without auth | GET https://qms-dashboard.replit.app/api/rbac/users (no cookie) | 401 Authentication required (not 404) | — | 17 | Admin |  | Not started | Prevents endpoint enumeration
98 | 98 | P0-Critical | Security — RBAC Enforcement | Non-admin cannot access admin endpoints | GET https://qms-dashboard.replit.app/api/rbac/users (dept_viewer session) | 401 or 403 (non-admin blocked) | Step 2 | 17 | Admin |  | Not started
99 | 99 | P0-Critical | Security — SQL Injection Prevention | Parameterized queries block injection | GET https://qms-dashboard.replit.app/api/dashboard?days=1;DROP TABLE-- | Safe response; no SQL error; days clamped to 1-365 | — | 17 | Admin |  | Not started | FIXED: make_interval with integer clamping
100 | 100 | P0-Critical | Security — Path Traversal Prevention | Screenshot endpoint blocks traversal | GET https://qms-dashboard.replit.app/api/kpis/docs/screenshots/../../etc/passwd | 400 error; file not served | — | 17 | Admin |  | Not started | FIXED: Sanitizes .., /, \ and enforces image extensions
101 | 101 | P0-Critical | Security — XSS Prevention | Input sanitizer strips HTML/script tags | POST https://qms-dashboard.replit.app/api/risks (title='<script>alert(1)</script>') | Tags stripped from saved data | — | 17 | Admin |  | Not started | inputSanitizer.ts strips HTML tags
102 | 102 | P1-High | Security — CSV Injection Prevention | CSV export prefixes formula characters | Export risks CSV with title starting with '=' | Exported value prefixed with single quote | Step 45 | 17 | Admin |  | Not started
103 | 103 | P1-High | Security — CSP Headers | Content-Security-Policy header present | Check response headers on any page | CSP header present; no unsafe-eval; frame-ancestors 'none' | — | 17 | Admin |  | Not started | unsafe-inline required for onclick handlers
104 | 104 | P1-High | Security — Security Headers | All security headers present | Check response headers | X-Frame-Options: DENY, X-Content-Type-Options: nosniff, etc. | — | 17 | Admin |  | Not started
105 | 105 | P1-High | Security — CORS Validation | CORS blocks unauthorized origins | OPTIONS with Origin: evil.com | No Access-Control-Allow-Origin for unauthorized origin | — | 17 | Admin |  | Not started
106 | 106 | P1-High | Security — OIDC Nonce Verification | Replay attack prevention via nonce | https://qms-dashboard.replit.app/api/callback | Mismatched nonce redirects to /login?error=invalid_nonce | Step 2 | 17 | Admin |  | Not started | FIXED: Nonce verified from oauth_data cookie
107 | 107 | P1-High | Security — Telegram Webhook Auth | Telegram webhook validates secret | POST https://qms-dashboard.replit.app/webhooks/telegram/action (no secret) | 401 Unauthorized when TELEGRAM_WEBHOOK_SECRET is set | — | 17 | Admin |  | Not started
108 | 108 | P1-High | Security — Linear Webhook Auth | Linear webhook validates header | POST https://qms-dashboard.replit.app/webhooks/linear (no Linear-Signature header) | 401 when LINEAR_WEBHOOK_SECRET is set and header missing | — | 17 | Admin |  | Not started | Header presence check; full HMAC planned
109 | 109 | P1-High | Security — UUID Obfuscation | API returns obfuscated IDs | GET https://qms-dashboard.replit.app/api/risks | Risk IDs use R-XXXXXXXX format, not sequential integers | Step 41 | 17 | Admin |  | Not started
110 | 110 | P1-High | Security — Generic Error Messages | No raw DB errors exposed | POST https://qms-dashboard.replit.app/api/risks (duplicate data) | Generic error message; no SQL/stack trace leaked | — | 17 | Admin |  | Not started | scrubErrorMessage() in inputSanitizer.ts
111 | 111 | P2-Medium | Onboarding — Flow | New user onboarding flow | https://qms-dashboard.replit.app/onboarding | Guided tour steps load for new users | Step 2 | 18 | Admin |  | Not started
112 | 112 | P2-Medium | Feedback — Submit | Feedback submission works | https://qms-dashboard.replit.app/feedback | Floating 'Give Feedback' button works; feedback saved | — | 18 | All |  | Not started | Button visible on every page
113 | 113 | P2-Medium | Guide — Public Access | User guide accessible without login | https://qms-dashboard.replit.app/guide | Guide page loads without authentication | — | 18 | All |  | Not started | Public endpoint
114 | 114 | P2-Medium | Accept Invite — Page | Invitation acceptance page | https://qms-dashboard.replit.app/accept-invite | Invite acceptance form loads (public) | — | 18 | All |  | Not started
115 | 115 | P1-High | PDPL Auth — Read Endpoints | PDPL reads require any auth | GET https://qms-dashboard.replit.app/api/pdpl/status (no auth) | 401 for unauthenticated; 200 for any authenticated user | Step 58 | 19 | Admin |  | Not started | Uses requireAuthOrKey
116 | 116 | P1-High | PDPL Auth — Write Endpoints | PDPL writes require write role | POST https://qms-dashboard.replit.app/api/pdpl/inventory (dept_viewer session) | 403 for read-only roles; 200 for write-capable roles | Step 59 | 19 | Admin |  | Not started | Uses requireWriteRole
117 | 117 | P1-High | Call Intel Auth — Ingest | Call ingest requires session or admin | POST https://qms-dashboard.replit.app/api/calls/ingest (no auth) | 401 without auth; 200 with session or admin key | Step 63 | 19 | Admin |  | Not started
118 | 118 | P1-High | Duplicate Radar Auth — Scan | Zoho scan requires admin | POST https://qms-dashboard.replit.app/api/duplicates/scan-zoho (non-admin) | 401 for non-admin users | Step 85 | 19 | Admin |  | Not started | Uses requireAdminOrKey
119 | 119 | P1-High | RBAC Auth — User Management | User CRUD requires admin | GET https://qms-dashboard.replit.app/api/rbac/users (non-admin) | 401 for non-admin users | Step 82 | 19 | Admin |  | Not started | Uses requireAdminOrKey
120 | 120 | P2-Medium | Zoho Region — Saudi (.sa) | Regional Zoho endpoint support | Set ZOHO_ACCOUNTS_URL=https://accounts.zoho.sa | CRM connects via .sa domain | Step 6 | 20 | Admin |  | Not started | FIXED: Uses env var with fallback

## 🔍 Expected Issues
Issue Coverage % →
🔍 Expected Issues — 75 failure modes ¦ Mark Y after testing confirms detection
Y = Yes, our tests would catch this ¦ N = No, would be missed ¦ Priority: P0=must-detect, P1=should-detect, P2=nice-to-detect
# | Priority | Category | Expected Issue (Business Description) | Would Our Tests Detect It? (Y/N) | Related Test # | Notes
1 | P0 | Integrations | CRM Leads connection is broken or data is not flowing in. | Y | 6 | Test #6 validates CRM Leads connection
2 | P0 | Integrations | CRM Deals connection is broken or data is not flowing in. | Y | 7 | Test #7 validates CRM Deals connection
3 | P1 | Integrations | Integrations status panel shows incorrect or missing system status. | Y | 10 | Test #10 checks /api/integrations/status
4 | P1 | Integrations | Zoho regional endpoint (.sa) not configured for Saudi accounts. | Y | 120 | Test #120 validates ZOHO_ACCOUNTS_URL
5 | P0 | Auth | Login page does not load or OIDC redirect fails. | Y | 1 | Test #1 validates login page
6 | P0 | Auth | OIDC callback fails — user cannot complete login. | Y | 2 | Test #2 validates callback flow
7 | P0 | Auth | Session cookie not set — user logged out immediately after login. | Y | 2,5 | Tests #2 and #5 validate session
8 | P0 | Auth | Admin API key login does not work. | Y | 3 | Test #3 validates admin key auth
9 | P0 | Auth | Unauthenticated user can access protected pages. | Y | 5,97 | Tests #5 and #97 validate auth enforcement
10 | P0 | Auth | OIDC nonce replay attack not prevented. | Y | 106 | Test #106 validates nonce verification
11 | P0 | Security | SQL injection via days parameter in trend/deadline queries. | Y | 99 | Test #99 validates parameterized queries
12 | P0 | Security | Path traversal via screenshot filename to read arbitrary files. | Y | 100 | Test #100 validates filename sanitization
13 | P0 | Security | XSS via unsanitized input stored and rendered. | Y | 101 | Test #101 validates HTML tag stripping
14 | P1 | Security | Rate limiter not blocking brute-force login attempts. | Y | 95-96 | Tests #95-96 validate rate limiting
15 | P1 | Security | RBAC bypass — non-admin accesses admin-only endpoints. | Y | 98,118-119 | Tests #98, 118, 119 validate RBAC
16 | P1 | Security | CSV export allows formula injection in Excel. | Y | 102 | Test #102 validates CSV sanitization
17 | P1 | Security | Missing Content-Security-Policy or security headers. | Y | 103-104 | Tests #103-104 validate headers
18 | P1 | Security | CORS allows unauthorized origins. | Y | 105 | Test #105 validates CORS
19 | P1 | Security | Telegram webhook accepts requests without secret. | Y | 107 | Test #107 validates webhook auth
20 | P1 | Security | Linear webhook accepts requests without signature header. | Y | 108 | Test #108 validates webhook auth
21 | P1 | Security | API exposes sequential integer IDs (enumeration risk). | Y | 109 | Test #109 validates UUID obfuscation
22 | P1 | Security | Raw database errors leaked in API responses. | Y | 110 | Test #110 validates error scrubbing
23 | P1 | Admin | Governance documents cannot be viewed or uploaded. | Y | 14 | Test #14 validates governance docs
24 | P1 | Admin | Scorecards cannot be viewed or created. | Y | 15 | Test #15 validates scorecards
25 | P1 | Admin | Activity log does not load. | Y | 16 | Test #16 validates activity log
26 | P1 | Admin | Audit runs list empty after running audits. | Y | 17 | Test #17 validates audit runs
27 | P1 | Admin | Automated triggers not listed. | Y | 18 | Test #18 validates triggers
28 | P0 | Quality Audit | Quality audit does not run or gets stuck. | Y | 19-20 | Tests #19-20 validate audit run + fallback
29 | P0 | Quality Audit | Audit results do not appear after completion. | Y | 23-25 | Tests #23-25 validate dashboard data
30 | P1 | Quality Audit | Triggers not firing after audit (NC, CAPA). | Y | 22 | Test #22 validates trigger chain
31 | P1 | Quality Audit | Email report not sent after audit. | Y | 21 | Test #21 validates email delivery
32 | P1 | Quality Audit | Audit uses fake/random data instead of live CRM. | Y | 19 | FIXED: Math.random() removed from crmComplianceTool
33 | P0 | Quality Dashboard | Main dashboard does not load or shows wrong score. | Y | 23
34 | P1 | Quality Dashboard | Run AI Audit button does not work. | Y | 27 | FIXED: Inngest fallback added
35 | P1 | Quality Dashboard | PDF export fails. | Y | 28
36 | P0 | QMS | QMS main page does not load. | Y | 29 | FIXED: Audit Runs card added
37 | P1 | QMS | CAPA list does not load or CAPA creation fails. | Y | 30-31
38 | P1 | QMS | NC creation fails or New NC button missing. | Y | 32-33 | FIXED: NC modal added
39 | P1 | QMS | Deal evaluations tab doesn't load. | Y | 34
40 | P1 | QMS | Trigger actions (acknowledge/dismiss) don't work. | Y | 37
41 | P0 | GRC | GRC Control Tower page does not load. | Y | 38 | FIXED: Audit readiness table added
42 | P1 | Risk Register | Risk list does not load. | Y | 41
43 | P1 | Risk Register | Risk treatment action update fails for UUID-based IDs. | Y | 44 | FIXED: UUID resolution corrected
44 | P1 | Risk Register | Heat map does not display correctly. | Y | 43
45 | P1 | Policy | Policy page JavaScript error prevents loading. | Y | 46 | FIXED: SyntaxError corrected
46 | P1 | Policy | GRC Approval button does not work. | Y | 49 | FIXED: Template literal corrected
47 | P1 | Policy | Policy lifecycle transitions fail. | Y | 48
48 | P1 | Compliance | Compliance list or summary does not load. | Y | 50-52
49 | P1 | Audit Readiness | Audit list or findings do not load. | Y | 53-54
50 | P1 | Vendor Risk | Vendor list or risk summary does not load. | Y | 56-57
51 | P1 | PDPL | PDPL status/data inventory does not load. | Y | 58-59 | FIXED: Nav init added
52 | P1 | PDPL | DSAR requests cannot be submitted. | Y | 60
53 | P1 | PDPL | Data incidents cannot be logged. | Y | 61
54 | P1 | PDPL | PDPL read endpoint accessible without auth. | Y | 115
55 | P1 | PDPL | PDPL write endpoint accessible with read-only role. | Y | 116
56 | P1 | Call Intelligence | Call records or analytics do not load. | Y | 63,65
57 | P1 | Call Intelligence | Call upload works without authentication. | Y | 117
58 | P1 | ROI | ROI initiatives or analytics do not load. | Y | 66,68
59 | P1 | Team | Team members list does not load. | Y | 69 | FIXED: Add Member button
60 | P2 | Team | Performance data missing. | Y | 71
61 | P1 | Projects | Projects list does not load. | Y | 73
62 | P1 | Event Logs | Event log list does not load. | Y | 76
63 | P2 | Event Logs | Silent failure when logging events (no error thrown). | Y | 76 | FIXED: Error now thrown on DB failure
64 | P2 | Data Migration | Import templates missing or import fails. | Y | 74
65 | P2 | Table F | Table F config/output not loading. | Y | 78-79
66 | P1 | Executive | Executive dashboard does not load or shows wrong data. | Y | 91-93 | FIXED: API parsing corrected
67 | P1 | Executive | Numbers don't match individual module screens. | Y | 94
68 | P1 | Scorecard | Scorecard snapshot does not load. | Y | 84
69 | P1 | Duplicate Radar | Duplicate summary does not load. | Y | 85
70 | P1 | Duplicate Radar | Zoho scan accessible to non-admin users. | Y | 118 | FIXED: requireAdminOrKey added
71 | P1 | Handoffs | Handoff rules or summary does not load. | Y | 87-88
72 | P1 | KPI | KPI list or summary does not load. | Y | 89-90
73 | P0 | Auth | Event log writes fake row on DB failure (audit integrity). | Y | — | FIXED: Error propagated instead of fake row
74 | P0 | Auth | Audit fallback does not fire all triggers. | Y | 22 | FIXED: directAuditRunner trigger chain corrected
75 | P1 | MBR Reports | MBR reports query wrong table names. | Y | — | FIXED: compliance_obligations→obligations, grc_audits→audits

## 👥 Adoption Tracker
Adoption % →
👥 Adoption Tracker — Mark Y / N / P for each area you use regularly (30 areas)
Y = Yes, using for real work at least weekly ¦ N = Not yet ¦ P = Partially (tried but not regular)
Area (Screen Name) | Primary Role | Sarah (Quality / GRC) | Mohammed Al Muzini (Quality / GRC) | GRQ Specialist | Admin | Other / Executive | Notes
Login & Authentication | All | N | N | N | N | N
Quality Dashboard (Home) | Quality | N | N | N | N | N
Run or Trigger Quality Audit | Quality | N | N | N | N | N
Admin — Governance & Scorecards | Admin | N | N | N | N | N
Admin — Activities / Audit Runs / Triggers | Admin | N | N | N | N | N
QMS Dashboard | Quality | N | N | N | N | N
GRC Control Tower | GRC | N | N | N | N | N
Risk Register | GRC | N | N | N | N | N
Policy Governance | GRC | N | N | N | N | N
Compliance Tracker | GRC | N | N | N | N | N
Audit Readiness | GRC | N | N | N | N | N
Vendor Risk Management | GRC | N | N | N | N | N
PDPL Privacy Compliance | GRC / GRQ | N | N | N | N | N
Data Migration (Import) | GRQ / GRC | N | N | N | N | N
Call Intelligence | Quality | N | N | N | N | N
ROI Evaluation | Quality | N | N | N | N | N
Team Performance | Quality | N | N | N | N | N
Project Portfolio (PMP) | Quality / GRQ | N | N | N | N | N
System Event Logs | All | N | N | N | N | N
Table F Engine | Quality / Admin | N | N | N | N | N
Sandbox | Quality / Admin | N | N | N | N | N
Users & Access Control | Admin | N | N | N | N | N
Scorecard | Quality | N | N | N | N | N
Duplicate Radar | Quality | N | N | N | N | N
Quality-GRC Handoffs | Quality / GRC | N | N | N | N | N
KPI Tracking | GRQ / Quality | N | N | N | N | N
Executive Dashboard | Quality / GRC / GRQ | N | N | N | N | N
Feedback | All | N | N | N | N | N
Onboarding | All | N | N | N | N | N
User Guide | All | N | N | N | N | N

## 🎯 Scenarios
Scenarios Completed → |  | / 100
🎯 Scenarios — 100 real-world tasks to build platform confidence
How to use: Read the Scenario. Follow the steps in 'How to Do It'. Mark Status as Done/Not done/Blocked.
# | Area | Scenario — You need to... | How to Do It in the Platform | Status
1 | Auth | You need to log in for the first time. | Go to the login page. Click 'Log in with Replit'. Authenticate via Google/GitHub/Apple/email. You are redirected to the Quality Dashboard. | Not done
2 | Auth | You need to log in as admin using API key. | Go to login page. Enter your ADMIN_API_KEY in the admin key field. Click login. You are redirected to the dashboard with admin access. | Not done
3 | Auth | You need to log out securely. | Click the logout button or POST to /api/logout. Your session cookie is cleared and you are redirected to the login page. | Not done
4 | Auth | A colleague says they can access pages without logging in. | Try opening /qms or /risks in an incognito window. Confirm you are redirected to /login. If not, report as a security issue. | Not done
5 | Auth | You suspect someone is brute-forcing the login page. | Try logging in 6+ times rapidly. After 5 attempts in 60 seconds, you should see a 429 Too Many Requests error. This confirms rate limiting. | Not done
6 | Auth | You need to verify your session is secure. | Open browser DevTools > Application > Cookies. Check that walaplus_session is HttpOnly, Secure, and SameSite=Lax. | Not done
7 | Auth | You need to check if the admin key cookie is set correctly. | After admin login, check cookies in DevTools. The admin_key cookie should be HttpOnly with 8-hour expiry. | Not done
8 | Auth | You need to confirm that OIDC nonce verification is working. | Complete a normal login. In the network tab, observe the callback redirects successfully. A tampered nonce would redirect to /login?error=invalid_nonce. | Not done
9 | Integrations | You need to check whether your CRM is properly connected before running an audit. | Go to /crm and verify Leads data loads. Also check GET /api/integrations/status for connection health. | Not done
10 | Integrations | You notice Deals data on the dashboard looks outdated. | Check /api/integrations/status. If Zoho shows errors, verify ZOHO_CLIENT_ID/SECRET/REFRESH_TOKEN in Replit Secrets. | Not done
11 | Integrations | A colleague asks if all systems feeding the platform are currently working. | Open /api/integrations/status. Share the JSON showing Zoho CRM, Google Calendar, and Email system statuses. | Not done
12 | Integrations | You want to confirm data is flowing before the weekly review. | Check /api/integrations/status. Verify CRM shows a recent sync time. Run AI Audit to force a fresh data pull. | Not done
13 | Integrations | Your Zoho account is in Saudi Arabia (.sa) region and CRM won't connect. | Set ZOHO_ACCOUNTS_URL=https://accounts.zoho.sa and ZOHO_API_DOMAIN=https://www.zohoapis.sa in Replit Secrets. Restart. | Not done
14 | Integrations | You need to browse individual CRM records for a specific lead. | Go to /crm, select the Leads tab. Click on a specific lead record to see its detailed fields and hygiene analysis. | Not done
15 | Admin | You need to update the scoring rules before the next audit. | Go to /admin. Open Governance Documents. Upload or edit the relevant document for Leads or Deals. | Not done
16 | Admin | A new product category was added and you need a new scorecard. | Go to /admin > Scorecards. Create a new scorecard with dimensions, criteria, and weights for the new category. | Not done
17 | Admin | You want to find out who changed a governance document last week. | Go to /admin > Activity Log. Filter or scroll to find entries from last week showing document changes. | Not done
18 | Admin | You need to check if this week's scheduled audit ran successfully. | Go to /admin > Audit Runs List. Find the most recent entry. Confirm status shows completed. | Not done
19 | Admin | The team wants to know what automatic audits are scheduled. | Go to /admin > Automated Triggers. Review trigger types, frequencies, and next scheduled times. | Not done
20 | Admin | You need to invite a new team member to the platform. | Go to /users. Click invite. Enter their email. They receive an invite link at /accept-invite. | Not done
21 | Admin | You need to change a user's role from viewer to Quality Manager. | Go to /users or GET /api/rbac/users. Find the user. Update their role via PUT /api/rbac/users/:id. | Not done
22 | Admin | You need to deactivate a former employee's access. | Go to /users. Find the user. Deactivate their account. Confirm they can no longer log in. | Not done
23 | Quality Audit | The monthly quality review is due and you need fresh audit data. | Go to /. Click 'Run AI Audit'. Wait for completion (~15s). Dashboard refreshes with new scores. | Not done
24 | Quality Audit | The Inngest dev server is not running but you need an audit. | Click 'Run AI Audit'. The system falls back to directAuditRunner automatically. Same results, no Inngest needed. | Not done
25 | Quality Audit | You want to confirm the audit email was sent. | Check the email inbox configured with RESEND_FROM_EMAIL. The quality report email should arrive within 1 minute. | Not done
26 | Quality Audit | You want to confirm all triggers fired after the audit. | Go to /qms > Triggers tab. Verify AUDIT_COMPLETED is present. If issues were found, NC_DETECTED and CAPA_REQUIRED too. | Not done
27 | Quality Audit | You want to see how scores changed over time. | Go to / > Audit History. Review the timeline of past audit runs with scores. | Not done
28 | Quality Audit | A manager asks for an on-demand audit of Leads only. | Run AI Audit from /. The audit automatically covers Leads (SDR agent) and Deals (Sales agent) in parallel. | Not done
29 | QMS | You want to check how many open CAPAs exist. | Go to /qms > CAPA tab. Count open/in-progress CAPAs. Note due dates for overdue items. | Not done
30 | QMS | You want to log a new nonconformance from an audit. | Go to /qms > NC tab. Click 'New NC'. Fill in title, type, severity, source, assigned_to. Click 'Create NC'. | Not done
31 | QMS | A manager asks for deal evaluation summaries. | Go to /qms > Deal Evaluations tab. Review quality evaluations for specific deals. | Not done
32 | QMS | You need to acknowledge an audit trigger. | Go to /qms > Triggers tab. Find the AUDIT_COMPLETED trigger. Click 'Acknowledge'. | Not done
33 | QMS | You need to create a CAPA for a critical finding. | Go to /qms > CAPA tab. Create new CAPA with type=corrective, root cause analysis, and action items. | Not done
34 | QMS | You want to check training assignments. | Go to /qms > Training tab. Review courses and their assignment status. | Not done
35 | QMS | You want to configure evaluation framework dimensions. | Go to /qms > Framework tab. Add/edit dimensions, criteria, weights, and pass thresholds. | Not done
36 | QMS | You want to view overall QMS health at a glance. | Open /qms. Review the summary cards: Evaluations, Open CAPA, Open NC, Training Completion, Audit Runs. | Not done
37 | GRC | Leadership asks for a one-page GRC status summary. | Open /grc. Review all summary cards: Risks, Policies, Compliance, Findings, Vendors, Controls. | Not done
38 | GRC | You want to check if any GRC area has a critical status. | Open /grc. Look for red/critical indicators on any card. Drill into that area for details. | Not done
39 | Risk Register | You need to add a newly identified operational risk. | Go to /risks. Click Add Risk. Fill in description, category, likelihood (1-4), impact (1-4). Save. | Not done
40 | Risk Register | The risk committee asks for a visual summary. | Open /risks > Heat Map. Share the 4x4 grid showing risk distribution by likelihood x impact. | Not done
41 | Risk Register | You need to create a treatment action for a risk. | Open a risk at /risks. Add a treatment action with type, owner, due date. Confirm it saves. | Not done
42 | Risk Register | You want to export all risks for offline review. | Go to /risks. Click Export CSV. Open the downloaded file and confirm all risks are included. | Not done
43 | Policy | You need to create a new data protection policy. | Go to /policies. Click New Policy. Fill in number, category, title, content, owner. Save as Draft. | Not done
44 | Policy | A policy needs GRC Manager approval before publishing. | Open the policy. Click 'Request GRC Approval'. GRC Manager approves. Then click 'Publish'. | Not done
45 | Policy | You want to check which policies are due for review. | Go to /policies. Look for policies with overdue review dates or filter by status. | Not done
46 | Compliance | A new regulation was published. You need to add it. | Go to /compliance. Add regulation with name, jurisdiction, effective date, requirements. | Not done
47 | Compliance | You need to check overdue compliance obligations. | Go to /compliance > Obligations. Filter for overdue items. Escalate as needed. | Not done
48 | Audit Readiness | An external auditor is coming. You need to see what's prepared. | Go to /audits. Find the upcoming audit. Review checklist completion and evidence pack status. | Not done
49 | PDPL | The DPO asks for the current PDPL compliance status. | Open /pdpl. Review the compliance status indicators and any outstanding obligations. | Not done
50 | PDPL | You need to record a new data processing activity. | Go to /pdpl > Data Inventory. Add a new entry with purpose, legal basis, data categories. | Not done
51 | PDPL | A data subject requests access to their data (DSAR). | Go to /pdpl. Submit a new DSAR request. Track its status (30-day SLA per PDPL Article 14). | Not done
52 | PDPL | A data breach has been detected. | Go to /pdpl. Log a new data incident with severity and details. Follow the 72-hour SDAIA notification timeline. | Not done
53 | PDPL | You want to verify AI guardrails are configured. | Check /api/pdpl/guardrails. Confirm PII masking patterns are present. | Not done
54 | Vendor Risk | You need to assess a new vendor's risk. | Go to /vendors. Add the vendor. Complete a risk assessment with security scoring. | Not done
55 | Vendor Risk | Procurement asks for a summary of high-risk vendors. | Go to /vendors. Filter or review the risk summary for High/Critical-rated vendors. | Not done
56 | Call Intelligence | Your manager asks for a call quality summary this week. | Go to /calls. Review analytics: call volume, QA scores, sentiment trends. | Not done
57 | Call Intelligence | You need to upload a call recording for analysis. | Go to /calls. Use the upload function to submit a recording. Wait for AI analysis results. | Not done
58 | ROI | Leadership asks which initiatives delivered the best ROI. | Go to /roi. Review analytics. Rank initiatives by ROI value. | Not done
59 | ROI | You need to create a new quality improvement initiative. | Go to /roi. Add new initiative with expected benefits, costs, and timeline. AI validates financial claims. | Not done
60 | Team | A team leader asks for quality scores of their team. | Go to /team > Overview. Review performance metrics and scores for the team. | Not done
61 | Team | You need to add a new team member. | Go to /team > Team Members. Click Add Member. Fill in name, email, role, department. Save. | Not done
62 | Team | HR asks for the complete team member list. | Go to /team > Team Members. Export or review the full list with roles and departments. | Not done
63 | Projects | You want to see all active improvement projects. | Go to /projects. Filter for active status. Review owner, milestones, and risks. | Not done
64 | Projects | A project has a scope change. You need to log it. | Go to /projects. Open the project. Add a change request with type and impact details. | Not done
65 | Event Logs | You need to investigate who deleted a record yesterday. | Go to /logs. Filter by yesterday's date and 'delete' action type. Identify the user. | Not done
66 | Event Logs | You want to confirm a scheduled audit ran on time. | Go to /logs. Search for audit trigger events. Confirm timestamp matches expected schedule. | Not done
67 | Scorecard | You want to compare quality scores across teams. | Go to /scorecard. Review snapshots per team/employee. Compare against targets. | Not done
68 | Duplicate Radar | You want to check duplicate leads before an import. | Go to /duplicates. Review duplicate cluster counts. Clean up before importing. | Not done
69 | Duplicate Radar | You want to run a fresh duplicate scan from Zoho. | POST /api/duplicates/scan-zoho (admin only). Wait for scan to complete. Review new clusters. | Not done
70 | KPI | You want to check if the team is on track for quarterly KPIs. | Go to /kpis. Review current values vs targets. Flag at-risk KPIs. | Not done
71 | KPI | A new KPI was approved. You need to add it. | Go to /kpis. Add new KPI with name, target, measurement frequency, and owner. | Not done
72 | Handoffs | A quality issue was escalated to GRC. You want to check its status. | Go to /api/handoff/events. Find the relevant handoff. Check its current status. | Not done
73 | Security | You want to verify rate limiting is working. | Open DevTools. Call GET /api/dashboard 11 times rapidly without auth. The 11th should return 429. | Not done
74 | Security | You want to test that SQL injection is blocked. | Try GET /api/dashboard?days=1;DROP TABLE--. The response should be normal (no error, days clamped). | Not done
75 | Security | You want to verify path traversal is blocked. | Try GET /api/kpis/docs/screenshots/../../etc/passwd. Should return 400 error, not file contents. | Not done
76 | Security | You want to check CSP headers are present. | Open DevTools > Network. Click any page request. Check Response Headers for Content-Security-Policy. | Not done
77 | Security | You want to verify non-admin users can't access RBAC endpoints. | Log in as a Department Viewer. Try GET /api/rbac/users. Should get 401. | Not done
78 | Security | You want to confirm error messages don't leak internal details. | Try creating a duplicate record. The error should be generic, not showing SQL constraint names. | Not done
79 | Security | You want to verify CORS blocks unauthorized origins. | Use curl with -H 'Origin: https://evil.com'. The response should not include Access-Control-Allow-Origin for that domain. | Not done
80 | Security | You want to confirm the Telegram webhook requires a secret. | POST to /webhooks/telegram/action without the secret parameter. Should get 401 if TELEGRAM_WEBHOOK_SECRET is set. | Not done
81 | Security | You want to verify IDs are obfuscated in API responses. | GET /api/risks. Risk IDs should use R-XXXXXXXX format, not sequential integers. | Not done
82 | Security | You want to verify XSS is prevented. | Create a risk with title '<script>alert(1)</script>'. View it. The script tags should be stripped. | Not done
83 | Security | You want to confirm CSV export sanitizes formula characters. | Create a record with title '=SUM(A1)'. Export to CSV. The cell should be prefixed with a single quote. | Not done
84 | Security | You want to verify the logout is POST-only. | Try GET /api/logout. Should fail or not clear session. Only POST should clear the session. | Not done
85 | Executive | The CEO asks for a one-screen summary before the board meeting. | Open /executive. Review Quality, Risk, Compliance, and KPI summaries. | Not done
86 | Executive | You want to verify Executive Dashboard numbers are accurate. | Compare a number (e.g., open risks) on /executive with the actual count on /risks. | Not done
87 | Executive | A board member asks how quality trended over the quarter. | Open /executive. Find the quality trend section. Share the 3-month trend chart. | Not done
88 | Cross-Module | You want to verify quality-to-GRC handoff rules. | Create a critical NC in /qms. Check if a corresponding handoff event appears in /api/handoff/events. | Not done
89 | Cross-Module | You want to verify the onboarding flow for new users. | Log in as a new user (or clear onboarding status). Go to /onboarding. Step through the guided tour. | Not done
90 | Cross-Module | You want to submit feedback about the platform. | Click the floating 'Give Feedback' button (bottom-right). Fill in and submit your feedback. | Not done
91 | Cross-Module | You want to check the user guide. | Go to /guide. Confirm it loads without requiring login (public page). | Not done
92 | Cross-Module | You need to verify the health check endpoint. | GET /api/health. Should return 200 OK with platform status. No auth required. | Not done
93 | Sandbox | You want to test features without affecting live data. | Go to /sandbox. Generate mock leads/deals. Confirm they don't appear in /crm (live data). | Not done
94 | Sandbox | A new team member wants to practice before going live. | Direct them to /sandbox. Have them explore dashboards using mock data. | Not done
95 | Sandbox | You want to test mock data generation. | GET /api/sandbox/leads and /api/sandbox/deals. Confirm mock data returns. | Not done
96 | Data Migration | You need to import leads from Excel. | Go to /migration. Download the import template. Fill it in. Upload and monitor the import job. | Not done
97 | Data Migration | An import job failed. You need to investigate. | Go to /migration. Find the failed job. Review error details. Fix the source file and retry. | Not done
98 | Data Migration | You want to check dedup rules before import. | Go to /migration. Review dedup rules to ensure duplicates won't be created. | Not done
99 | Table F | You want to confirm Table F classifies leads correctly. | Go to /tablef. Review output for sample records. Confirm categories match governance rules. | Not done
100 | Table F | A new governance rule was added. Verify Table F uses it. | Upload the updated governance doc. Run Table F processing. Check output includes the new rule. | Not done