## 📊 Summary Dashboard
WalaPlus Platform — Testing & Adoption Tracker
25-Day Testing & Adoption Plan ¦ Team: Sara & Mohammed Al Muzini ¦ Team Size: 2
LIVE METRICS — auto-calculated from the tracker sheets
| Test Completion | Issue Coverage | Team Adoption
| 24.5902 | 0 | 0
| Target: 100% by Day 25 | Target: ≥ 80% | Target: ≥ 50%
HOW TO USE THIS WORKBOOK
📋 Sheet 2 — Testing Tracker: Go through each row and change Status to: Not started ¦ In progress ¦ Done ¦ Blocked. Add a note if blocked.
👥 Sheet 3 — Adoption Tracker: Each person marks Y (Yes), N (Not yet), or P (Partially) for the areas they use for real work.
🔍 Sheet 4 — Expected Issues: After testing, mark Y or N for each issue — this drives the Issue Coverage % above.
📊 This Summary Dashboard updates automatically as you fill in the other sheets. No manual calculation needed.
🎯 Sheet 5 — Scenarios: 100 real-world tasks. Work through 4–5 per day. Mark Status = Done when you have completed each one in the live platform. This drives adoption.

## 🧪 Testing Tracker
Test Completion % → | 24.5902
🧪 Testing Tracker — 61 tests · 100% platform coverage ¦ Follow Sequence order
Smart order: Steps 1–3 Integrations → Steps 4–8 Admin → Step 9 Run Audit → Steps 10–14 Quality Dashboard → Steps 15–16 AI Quality → Steps 17–61 all other areas ¦ Status: Not started ¦ In progress ¦ Done ¦ Blocked
Seq | # | Area (Screen Name) | What We Are Checking (Business Case) | Do This After | Phase (Day) | Suggested Owner | Responsible Person | Status | Notes
1 | 1 | Integrations — CRM Leads | We can confirm the connection to the CRM is working and Leads data is flowing in correctly. | — | 1 | Quality / Admin | Sarah Hijazi | Blocked | whiting for real data
2 | 2 | Integrations — CRM Deals | We can confirm the connection to the CRM is working and Deals data is flowing in correctly. | Step 1 | 1 | Quality / Admin | Sarah Hijazi | Blocked | whiting for real data
3 | 3 | Integrations — Status Overview | We can see the overall integrations status panel and confirm all connected systems are shown. | Steps 1–2 | 1 | Quality / Admin | Sarah Hijazi | Blocked | whiting for real data
4 | 4 | Admin Panel — Governance Documents | We can view and manage the rules documents (governance documents) used for Leads and Deals. | Step 3 | 2 | Quality / Admin | Sarah Hijazi | NOTE | whiting for real data
5 | 5 | Admin Panel — Scorecards | We can view and manage the scorecards (e.g. for SDR/Leads and Sales/Deals). | Step 4 | 2 | Quality / Admin | Sarah Hijazi | NOTE | whiting for real data
6 | 6 | Admin Panel — Activity Log | We can see a log of admin activities — who did what and when. | Step 5 | 2 | Quality / Admin | Sarah Hijazi | NOTE | whiting for real data
7 | 7 | Admin Panel — Audit Runs List | We can see the list of quality audit runs (workflow runs). | Step 5 | 2 | Quality / Admin | Sarah Hijazi | NOTE | whiting for real data
8 | 8 | Admin Panel — Automated Triggers | We can see the list of automated triggers (e.g. scheduled audits). | Steps 5–7 | 2, 20 | Quality / Admin | Sarah Hijazi | NOTE | whiting for real data
9 | 9 | Quality Audit (AI) — Full Run | We can run a full quality audit and see results for both Leads (SDR) and Deals (Sales). This step must be done before testing the Quality Dashboard so there is real data to display. | Steps 4–8 | 3 | Quality | Sarah Hijazi | NOTE | whiting for real data
10 | 10 | Quality Dashboard — Main Page | The main page opens and shows our overall quality score and the main numbers we need. | Step 9 | 1 | Quality |  | NOTE | whiting for real data
11 | 11 | Quality Dashboard — Latest Audit Result | We can see the result of the most recent quality audit (or a clear message if none yet). | Step 9 | 1 | Quality |  | NOTE | whiting for real data
12 | 12 | Quality Dashboard — Audit History | We can see the history of past audits (list or timeline). | Step 9 | 1 | Quality |  | NOTE | whiting for real data
13 | 13 | Quality Dashboard — AI Agent Performance | We can see how the AI quality agents are performing (or a clear message if not set up). | Step 9 | 1 | Quality |  | NOTE | whiting for real data
14 | 14 | Quality Dashboard — Integrations Status | We can see whether connections to CRM and other systems are working (integrations status panel on the dashboard). | Steps 3, 9 | 1, 5 | Quality |  | NOTE | whiting for real data
15 | 15 | AI Quality — Leads (SDR) | When we run an audit, the system checks Leads (SDR) using the right rules and scorecard; results appear on the dashboard. | Steps 4–9 | 22 | Quality |  | NOTE | whiting for real data
16 | 16 | AI Quality — Deals (Sales) | When we run an audit, the system checks Deals (Sales) using the right rules and scorecard; results appear on the dashboard. | Steps 4–9 | 23 | Quality |  | NOTE | whiting for real data
17 | 17 | QMS Dashboard — Main Page | The QMS main page opens and shows the main quality management numbers. | Step 9 | 6 | Quality |  | In progress | All Audits number shall be added inside the main quality numbers
18 | 18 | QMS Dashboard — CAPA List | We can see the list of corrective and preventive actions (CAPA). | Step 17 | 6 | Quality |  | Not started | i dont now how
19 | 19 | QMS Dashboard — Nonconformances (NC) | We can see the list of nonconformances (NC). | Step 17 | 6 | Quality |  | Not started | i dont now how
20 | 20 | QMS Dashboard — Deal Evaluations | We can see deal evaluations (e.g. quality evaluations of deals). | Step 17 | 6 | Quality |  | Not started | i dont now how
21 | 21 | GRC Control Tower — Main Page | The GRC main page opens and shows summaries: risks, compliance, policies, audits, vendors. | — | 7 | GRC | Mohammed AlMuzaini | NOTE | there is no audit in GRC main page
22 | 22 | Risk Register — Risk List | We can see the list of risks. | Step 21 | 8 | GRC | Mohammed AlMuzaini | Done
23 | 23 | Risk Register — Heat Map | We can see the risk heat map (visual view of risk levels). | Step 22 | 8 | GRC | Mohammed AlMuzaini | Done
24 | 24 | Risk Register — Risk Categories | We can see risk categories (how risks are grouped). | Step 22 | 8 | GRC | Mohammed AlMuzaini | Done | they add more than one risk
25 | 25 | Policy Governance — Policy List | We can see the list of policies. | Step 21 | 9 | GRC | Mohammed AlMuzaini | NOTE | we can't add policy
26 | 26 | Policy Governance — Policy Summary | We can see the policy summary (high-level view). | Step 25 | 9 | GRC | Mohammed AlMuzaini | Blocked | there is no policy add
27 | 27 | Compliance Tracker — Regulations List | We can see the list of regulations we track. | Step 21 | 9 | GRC | Mohammed AlMuzaini | Done
28 | 28 | Compliance Tracker — Obligations List | We can see the list of compliance obligations. | Step 27 | 9 | GRC | Mohammed AlMuzaini | Done
29 | 29 | Compliance Tracker — Compliance Summary | We can see the compliance summary (overall status). | Step 27 | 9 | GRC | Mohammed AlMuzaini | Done
30 | 30 | Audit Readiness — Audit List | We can see the list of audits (internal/external). | Step 21 | 11 | GRC | Mohammed AlMuzaini | Blocked | is no audit in GRC main page
31 | 31 | Audit Readiness — Audit Findings | We can see audit findings. | Step 30 | 11 | GRC | Mohammed AlMuzaini | Blocked | is no audit in GRC main page
32 | 32 | Vendor Risk Management — Vendor List | We can see the list of vendors. | Step 21 | 11 | GRC | Mohammed AlMuzaini | Done
33 | 33 | Vendor Risk Management — Vendor Risk Summary | We can see the vendor risk summary. | Step 32 | 11 | GRC | Mohammed AlMuzaini | Done
34 | 34 | Data Migration — Import Templates | We can see the ready-made templates for importing data from Excel/spreadsheets. | — | 12 | GRQ / GRC | Sarah Hijazi | Not started | i dont now how
35 | 35 | Data Migration — Import Jobs List | We can see the list of past or current import jobs. | Step 34 | 12 | GRQ / GRC | Sarah Hijazi | Not started | i dont now how
36 | 36 | Data Migration — Deduplication Rules | We can see the rules used to avoid importing duplicate leads or deals. | Step 34 | 12 | GRQ / GRC | Sarah Hijazi | Not started | i dont now how
37 | 37 | Call Intelligence — Call Records | We can see the list of call records. | Step 9 | 13 | Quality |  | NOTE | Where is calls, Five9? Directly or it will be downloaded, then uploaded?
38 | 38 | Call Intelligence — Call Analytics | We can see call analytics (e.g. summaries, trends). | Step 37 | 13 | Quality |  | Done
39 | 39 | ROI Evaluation — Initiatives List | We can see the list of ROI initiatives. | — | 13 | Quality |  | Not started | i dont now how
40 | 40 | ROI Evaluation — ROI Analytics | We can see ROI analytics (e.g. summaries, trends). | Step 39 | 13 | Quality |  | Not started | i dont now how
41 | 41 | Team Performance — Team Members List | We can see the list of team members. | — | 14 | Quality |  | Blocked | I Can't see where they are
42 | 42 | Team Performance — Performance Data | We can see team performance data (e.g. scores, metrics). | Step 41 | 14 | Quality |  | Blocked | I Can't see where they are
43 | 43 | Project Portfolio (PMP) — Projects List | We can see the list of projects. | — | 14 | Quality / GRQ | Mohammed AlMuzaini | Done
44 | 44 | System Event Logs — Events List | We can see the list of system events (who did what, when). | — | 14 | All | Mohammed AlMuzaini | NOTE | NO DATA
45 | 45 | System Event Logs — Log Statistics | We can see log statistics (e.g. counts, summaries). | Step 44 | 14 | All |  | Not started | i dont now how
46 | 46 | Table F Engine — Configuration View | We can see the Table F engine configuration and confirm the rules are set up correctly for our data. | Steps 4–5 | 15 | Quality / Admin |  | NOTE | there is no data
47 | 47 | Table F Engine — Data Processing Check | We can confirm that Table F processes and categorises our data as expected (no missing or wrongly classified records). | Step 46 | 15 | Quality / Admin |  | NOTE | there is no data
48 | 48 | Table F Engine — Output / Results View | We can see the output and results produced by Table F and they match what we expect. | Step 47 | 15 | Quality / Admin |  | NOTE | there is no data
49 | 49 | Sandbox — Test Environment Access | We can access the sandbox (test) environment and confirm it is separate from live data. | — | 15 | Quality / Admin |  | Not started | No Need
50 | 50 | Sandbox — Test Run | We can run a test scenario in the sandbox and confirm results appear correctly without affecting live data. | Step 49 | 15 | Quality / Admin |  | Not started | No Need
51 | 51 | PDPL Privacy Compliance — Compliance Status | We can see the PDPL compliance status. | — | 16 | GRC / GRQ | Mohammed AlMuzaini | Blocked | WHERE WE CAN ADD THE PDPL?
52 | 52 | PDPL Privacy Compliance — Data Inventory | We can see the data inventory (what personal data we hold and where). | Step 51 | 16 | GRC / GRQ | Mohammed AlMuzaini | Blocked | WHERE WE CAN ADD THE PDPL?
53 | 53 | Users & Access Control — User Statistics | We can see user statistics (e.g. how many users, roles). | — | 17 | Admin | Sarah Hijazi | Not started | i dont now how
54 | 54 | Scorecard — Snapshot | We can see the current scorecard snapshot (quality scores at a point in time). | Step 9 | 18 | Quality | Sarah Hijazi | Not started | i dont now how
55 | 55 | Duplicate Radar — Duplicate Summary | We can see the duplicate summary (e.g. how many duplicate leads/deals, trends). | Steps 1–2 | 18 | Quality | Sarah Hijazi | Done
56 | 56 | Quality–GRC Handoffs — Handoff Rules | We can see the list of handoff rules (when quality issues go to GRC). | Steps 9, 21 | 19 | Quality / GRC |  | Blocked | NO DATA
57 | 57 | Quality–GRC Handoffs — Handoff Summary | We can see the handoff summary (e.g. counts, status). | Step 56 | 19 | Quality / GRC |  | Blocked | NO DATA
58 | 58 | KPI Tracking — KPI List | We can see the list of KPIs. | — | 19 | GRQ / Quality |  | Done
59 | 59 | KPI Tracking — KPI Summary | We can see the KPI summary (e.g. overall performance vs targets). | Step 58 | 19 | GRQ / Quality |  | Done
60 | 60 | Executive Dashboard — Main View | We can see the Executive Dashboard and it shows the key top-level summaries across quality, GRC, and performance. | Steps 9, 21 | 24 | Quality / GRC / GRQ |  | Done
61 | 61 | Executive Dashboard — Data Accuracy Check | The numbers shown on the Executive Dashboard match what we see in the individual area screens (no discrepancies). | Step 60 | 25 | Quality / GRC / GRQ |  | Done

## 👥 Adoption Tracker
Adoption % → | 0
👥 Adoption Tracker — Mark Y / N / P for each area you use for real work
Y = Yes, using for real work at least weekly ¦ N = Not yet ¦ P = Partially (explored but not daily use) ¦ Primary Role = who typically owns the area
Area (Screen Name) | Primary Role | Sarah (Quality / GRC) | Mohammed Al Muzini (Quality / GRC) | GRQ Specialist | Admin | Other / Executive | Notes
Quality Dashboard (Home) | Quality | N | N | N | N | N
Run or Trigger Quality Audit | Quality | N | N | N | N | N
Admin — Governance & Scorecards | Quality / Admin | N | N | N | N | N
Admin — Activities / Audit Runs / Triggers | Quality / Admin | N | N | N | N | N
QMS Dashboard | Quality | N | N | N | N | N
GRC Control Tower | GRC | N | N | N | N | N
Risk Register | GRC | N | N | N | N | N
Policy Governance | GRC | N | N | N | N | N
Compliance Tracker | GRC | N | N | N | N | N
Audit Readiness | GRC | N | N | N | N | N
Vendor Risk Management | GRC | N | N | N | N | N
Data Migration (Import) | GRQ / GRC | N | N | N | N | N
Call Intelligence | Quality | N | N | N | N | N
ROI Evaluation | Quality | N | N | N | N | N
Team Performance | Quality | N | N | N | N | N
Project Portfolio (PMP) | Quality / GRQ | N | N | N | N | N
System Event Logs | All | N | N | N | N | N
Table F Engine | Quality / Admin | N | N | N | N | N
Sandbox | Quality / Admin | N | N | N | N | N
PDPL Privacy Compliance | GRC / GRQ | N | N | N | N | N
Users & Access Control | Admin | N | N | N | N | N
Scorecard | Quality | N | N | N | N | N
Duplicate Radar | Quality | N | N | N | N | N
Quality–GRC Handoffs | Quality / GRC | N | N | N | N | N
KPI Tracking | GRQ / Quality | N | N | N | N | N
Executive Dashboard | Quality / GRC / GRQ | N | N | N | N | N

## 🔍 Expected Issues
Issue Coverage % → | 0
🔍 Expected Issues — 49 failure modes ¦ Mark Y after testing if our tests would catch each one
Y = Yes, our tests would catch this ¦ N = No, would be missed ¦ Target: at least 40 of 49 = Y (≥ 80%)
# | Category | Expected Issue (Business Description) | Would Our Tests Detect It? (Y / N) | Notes
1 | Integrations | CRM Leads connection is broken or data is not flowing in. | N
2 | Integrations | CRM Deals connection is broken or data is not flowing in. | N
3 | Integrations | Integrations status panel shows incorrect or missing system status. | N
4 | Admin | Governance documents cannot be viewed or are missing. | N
5 | Admin | Scorecards cannot be viewed, are wrong, or are missing. | N
6 | Admin | Activity log does not load or is missing entries. | N
7 | Admin | Audit runs list is empty or shows incorrect entries. | N
8 | Admin | Automated triggers are not listed or show wrong schedules. | N
9 | Admin | Admin changes do not save or take effect correctly. | N
10 | Quality Audit | Quality audit does not run or gets stuck. | N
11 | Quality Audit | Audit results do not appear after a run is completed. | N
12 | Quality Dashboard | Main dashboard does not load or shows wrong overall score. | N
13 | Quality Dashboard | Latest audit result is missing or outdated on the dashboard. | N
14 | Quality Dashboard | Audit history is empty or missing past entries. | N
15 | Quality Dashboard | AI agent performance data is missing or incorrect. | N
16 | Quality Dashboard | Integrations status on the dashboard is wrong or not updating. | N
17 | AI Quality | AI audit for Leads (SDR) does not run or produces wrong results. | N
18 | AI Quality | AI audit for Deals (Sales) does not run or produces wrong results. | N
19 | QMS | QMS main page does not load or shows wrong numbers. | N
20 | QMS | CAPA list does not load or is missing entries. | N
21 | QMS | Nonconformances (NC) list does not load or is incomplete. | N
22 | QMS | Deal evaluations do not appear or are incorrect. | N
23 | GRC | GRC Control Tower main page does not load or shows wrong summaries. | N
24 | Risk Register | Risk list does not load or is missing risks. | N
25 | Risk Register | Risk heat map does not display correctly. | N
26 | Risk Register | Risk categories are missing or incorrectly grouped. | N
27 | Policy Governance | Policy list does not load or policies are missing. | N
28 | Compliance Tracker | Compliance list or summary does not load or is wrong. | N
29 | Audit Readiness | Audit list or findings do not load. | N
30 | Vendor Risk | Vendor list or risk summary does not load. | N
31 | Data Migration | Import templates are missing or cannot be downloaded. | N
32 | Call Intelligence | Call records or analytics do not load. | N
33 | ROI Evaluation | ROI initiatives or analytics do not load. | N
34 | Team Performance | Team members list or performance data does not load. | N
35 | Project Portfolio | Projects list does not load. | N
36 | System Event Logs | Event log list or statistics do not load. | N
37 | Table F Engine | Table F configuration cannot be viewed or is incorrect. | N
38 | Table F Engine | Table F output or results do not match expected data. | N
39 | Sandbox | Sandbox environment cannot be accessed or is not separated from live data. | N
40 | Sandbox | Test run in sandbox affects or leaks into live data. | N
41 | PDPL | PDPL compliance status or data inventory does not load. | N
42 | Users & Access | User statistics do not load or are incorrect. | N
43 | Users & Access | A user can access an area they should not have permission for. | N
44 | Scorecard | Scorecard snapshot does not load or shows wrong scores. | N
45 | Duplicate Radar | Duplicate summary does not load or shows wrong counts. | N
46 | Quality–GRC Handoffs | Handoff rules or summary do not load. | N
47 | KPI Tracking | KPI list or summary does not load or shows wrong targets. | N
48 | Executive Dashboard | Executive Dashboard does not load or shows wrong summaries. | N
49 | Executive Dashboard | Numbers on Executive Dashboard do not match individual area screens. | N

## 🎯 Scenarios
Scenarios Completed → | 0 | / 100
🎯 Scenarios — 100 real-world tasks to build platform confidence ¦ Work through 4–5 per day and mark Done when completed
How to use: Read the Scenario. Follow the steps in 'How to Do It in the Platform'. When you have completed it in the real platform, change Status to Done. Status: Not done ¦ Done
# | Area | Scenario — You need to... | How to Do It in the Platform | Status
1 | Integrations | You need to check whether your CRM is properly connected before running an audit. | Go to the Integrations area and look at the CRM Leads connection status. Confirm it shows as connected and that data was received recently. | Not done
2 | Integrations | You notice that Deals data on the dashboard looks outdated. | Go to Integrations, check the CRM Deals connection. If it shows an error, contact your admin to refresh or reconnect. | Not done
3 | Integrations | A colleague asks if all systems feeding the platform are currently working. | Open the Integrations Status Overview panel and share the summary showing which systems are connected, disconnected, or pending. | Not done
4 | Integrations | You want to confirm data is flowing before the weekly team review. | Open Integrations status, check that CRM Leads and CRM Deals both show a recent sync time. If not, raise with Admin before the meeting. | Not done
5 | Admin — Governance & Scorecards | You need to update the scoring rules before the next audit. | Go to Admin Panel, open Governance Documents. Find the relevant document for Leads or Deals and review the current rules. Make changes as permitted. | Not done
6 | Admin — Governance & Scorecards | A new product category was added and you need a new scorecard. | Go to Admin Panel → Scorecards. Check if the category is already listed. If not, create or request a new scorecard for SDR/Leads or Sales/Deals. | Not done
7 | Admin — Activities / Audit Runs / Triggers | You want to find out who changed a governance document last week. | Open Admin Panel → Activity Log. Filter or scroll to find entries from last week. Look for document change events and note the user name and timestamp. | Not done
8 | Admin — Activities / Audit Runs / Triggers | You need to check if this week's scheduled audit ran successfully. | Go to Admin Panel → Audit Runs List. Find the most recent entry. Confirm the status shows completed and check the result summary. | Not done
9 | Admin — Activities / Audit Runs / Triggers | The team wants to know what automatic audits are scheduled for this month. | Open Admin Panel → Automated Triggers. Review the list of triggers, their frequency, and next scheduled run dates. | Not done
10 | Admin — Activities / Audit Runs / Triggers | You need to add a new weekly audit trigger for a new business area. | Go to Admin Panel → Automated Triggers. Select to add a new trigger, set the area (Leads or Deals), choose the schedule (weekly), and save. | Not done
11 | Run Quality Audit | The monthly quality review is due and you need fresh audit data. | Go to Quality Audit (AI). Select the scope (Leads, Deals, or both). Click Run Audit. Wait for the process to finish and confirm results appear on the Quality Dashboard. | Not done
12 | Run Quality Audit | You want to test a new scorecard before it goes live. | Run a quality audit in the Sandbox environment first (not live). Check results against the expected scores for the new scorecard. | Not done
13 | Run Quality Audit | A manager asks for an on-demand audit of last week's Deals. | Go to Quality Audit (AI), filter or set the date range for last week's Deals, run the audit, and share the results link with the manager. | Not done
14 | Quality Dashboard | You want a quick view of the overall quality health before a leadership meeting. | Open the Quality Dashboard home page. Note the overall quality score, the latest audit result, and any areas flagged in red. | Not done
15 | Quality Dashboard | You need to compare quality scores from this month vs last month. | Go to Quality Dashboard → Audit History. Look at the timeline or list of past audits. Compare the scores between the two periods. | Not done
16 | Quality Dashboard | A team member asks how the AI quality agents are performing. | Open Quality Dashboard → AI Agent Performance section. Share the current performance summary, noting any agents flagged as underperforming. | Not done
17 | Quality Dashboard | You want to confirm the dashboard is showing the most recent audit. | Check the 'Latest Audit Result' section on the Quality Dashboard. Confirm the date shown matches the most recent audit run. If not, re-run or refresh. | Not done
18 | Quality Dashboard | You need to check if CRM integrations are healthy from the dashboard. | Look at the Integrations Status section on the Quality Dashboard. Confirm all connected systems show green/active status. | Not done
19 | AI Quality — Leads | You want to review how well SDR Leads were qualified this week. | Run or open the latest AI Quality audit for Leads (SDR). Review the scorecard results, identify the lowest-scoring criteria, and share the report. | Not done
20 | AI Quality — Leads | A specific SDR's Leads are flagged for low quality. You need to investigate. | Open AI Quality → Leads results. Filter by the SDR's name. Review the individual lead scores and the specific criteria that failed. | Not done
21 | AI Quality — Deals | You want to check quality scores for Deals closed this quarter. | Run or open the AI Quality audit for Deals (Sales). Filter by date range for the quarter. Review overall scores and flag low-quality deals for follow-up. | Not done
22 | AI Quality — Deals | A sales rep disputes a low quality score on one of their deals. | Open AI Quality → Deals results. Find the specific deal by name or ID. Review the detailed scorecard breakdown and share the criteria that led to the low score. | Not done
23 | QMS Dashboard | You need to check how many open CAPAs exist right now. | Open QMS Dashboard → CAPA List. Count or filter for open/in-progress CAPAs. Note due dates for any overdue items. | Not done
24 | QMS Dashboard | You want to log a new nonconformance found during an audit. | Go to QMS Dashboard → Nonconformances (NC). Create a new NC entry. Fill in the description, category, and assign it to the responsible team. | Not done
25 | QMS Dashboard | A manager asks for a summary of deal quality evaluations this quarter. | Open QMS Dashboard → Deal Evaluations. Filter by date range. Export or screenshot the summary for the manager. | Not done
26 | QMS Dashboard | You need to track the progress of a CAPA that was opened last month. | Go to QMS Dashboard → CAPA List. Find the CAPA by name or date. Check its current status and any progress notes. | Not done
27 | QMS Dashboard | You want to see the QMS overall health at a glance. | Open the QMS Dashboard main page. Review the summary numbers — open CAPAs, open NCs, overdue items — and flag any that need immediate attention. | Not done
28 | GRC Control Tower | Leadership asks for a one-page GRC status summary. | Open the GRC Control Tower main page. Review the summaries for Risks, Compliance, Policies, Audits, and Vendors. Screenshot or export for the report. | Not done
29 | GRC Control Tower | You want to check if any GRC area has a critical status before the board meeting. | Open GRC Control Tower. Look for any area showing a red or critical indicator. Drill into that area for details. | Not done
30 | GRC Control Tower | A new team member joins the GRC team and needs an overview of all active areas. | Walk them through the GRC Control Tower main page, explaining each summary card: risks, compliance, policies, audit readiness, and vendor status. | Not done
31 | Risk Register | You need to add a newly identified operational risk. | Go to Risk Register → Risk List. Add a new risk entry with description, category, likelihood, impact, and owner. | Not done
32 | Risk Register | The risk committee asks for a visual summary of risk levels. | Open Risk Register → Heat Map. Share the current view showing high, medium, and low risks plotted by likelihood and impact. | Not done
33 | Risk Register | You want to check which risk category has the most open items. | Go to Risk Register → Risk Categories. Review the breakdown. Note the category with the highest count and flag it for the next risk meeting. | Not done
34 | Risk Register | A risk owner asks what risks are assigned to them. | Open Risk Register → Risk List. Filter by owner name. Share the filtered list with due dates and current status. | Not done
35 | Policy Governance | You need to find the current version of the data protection policy. | Go to Policy Governance → Policy List. Search or scroll for the data protection policy. Open it to confirm the version date and current status. | Not done
36 | Policy Governance | A policy is due for annual review. You need to flag it. | Open Policy Governance → Policy List. Find the policy. Update its review date or add a note flagging it for review. Notify the policy owner. | Not done
37 | Policy Governance | You want a high-level view of all active vs. expired policies. | Open Policy Governance → Policy Summary. Review the breakdown of active, under review, and expired policies. Flag any expired ones for urgent action. | Not done
38 | Compliance Tracker | A new regulation was published and you need to add it to the tracker. | Go to Compliance Tracker → Regulations List. Add a new regulation entry with name, jurisdiction, effective date, and assigned owner. | Not done
39 | Compliance Tracker | You need to check which compliance obligations are overdue. | Open Compliance Tracker → Obligations List. Filter for overdue or past-due items. Share the list with the compliance lead. | Not done
40 | Compliance Tracker | The compliance committee asks for the overall compliance status. | Open Compliance Tracker → Compliance Summary. Review the overall status score and the breakdown by regulation. Share or export for the committee. | Not done
41 | Compliance Tracker | You want to confirm all obligations linked to PDPL are being tracked. | Go to Compliance Tracker → Obligations List. Filter by regulation = PDPL. Confirm all required obligations are listed with owners and due dates. | Not done
42 | Audit Readiness | An external auditor is coming next month. You need to see what is prepared. | Open Audit Readiness → Audit List. Find the upcoming external audit entry. Review what documents and evidence have been submitted so far. | Not done
43 | Audit Readiness | You want to log a new finding from an internal audit. | Go to Audit Readiness → Audit Findings. Add a new finding with description, severity, audit name, and assigned owner for resolution. | Not done
44 | Audit Readiness | A manager asks how many open audit findings exist. | Open Audit Readiness → Audit Findings. Filter for open/unresolved findings. Count them and share the list sorted by severity. | Not done
45 | Vendor Risk Management | You need to check the risk level of a new vendor before approval. | Go to Vendor Risk Management → Vendor List. Find the vendor (or add it if new). Review or assign the risk rating. | Not done
46 | Vendor Risk Management | The procurement team asks for a summary of high-risk vendors. | Open Vendor Risk Management → Vendor Risk Summary. Filter or note vendors rated high risk. Share the list with procurement. | Not done
47 | Vendor Risk Management | A vendor's contract is up for renewal. You need to review their risk profile. | Go to Vendor Risk Management → Vendor List. Find the vendor. Review their current risk score, last assessment date, and any open issues. | Not done
48 | Data Migration | You need to import a batch of new leads from an Excel file. | Go to Data Migration (Import). Download the Leads import template. Fill it in with your data. Upload it and check the import job status. | Not done
49 | Data Migration | You want to check if last week's import job completed successfully. | Go to Data Migration → Import Jobs List. Find last week's job. Confirm the status shows completed and check the number of records imported vs. errors. | Not done
50 | Data Migration | You want to make sure duplicate leads won't be created during import. | Before importing, go to Data Migration → Deduplication Rules. Confirm the dedup rules are set to check for existing leads by email or phone. | Not done
51 | Data Migration | An import job failed. You need to understand why. | Open Data Migration → Import Jobs List. Find the failed job. Review the error details. Correct the file and re-upload. | Not done
52 | Call Intelligence | Your manager asks for a summary of call quality this week. | Open Call Intelligence → Call Analytics. Filter for this week. Review call volume, average quality scores, and any flagged calls. | Not done
53 | Call Intelligence | You want to listen to a specific call flagged for low quality. | Go to Call Intelligence → Call Records. Search for the call by agent name, date, or lead name. Open the record and review the quality notes. | Not done
54 | Call Intelligence | You need to identify which agents had the lowest call quality last month. | Open Call Intelligence → Call Analytics. Filter by last month. Sort agents by quality score ascending. Note the bottom performers for coaching. | Not done
55 | ROI Evaluation | Leadership asks which quality initiatives delivered the best ROI this year. | Open ROI Evaluation → ROI Analytics. Filter by year. Review and rank initiatives by ROI value. Export the top performers for the presentation. | Not done
56 | ROI Evaluation | You need to add a new quality improvement initiative to track its ROI. | Go to ROI Evaluation → Initiatives List. Add a new initiative with name, expected benefit, cost, and start date. | Not done
57 | ROI Evaluation | You want to check whether a completed initiative delivered its expected ROI. | Open ROI Evaluation → Initiatives List. Find the completed initiative. Compare actual ROI vs. the expected target. | Not done
58 | Team Performance | A team leader asks for the quality scores of their team this month. | Open Team Performance → Performance Data. Filter by team or team leader. Review the quality scores and share the summary. | Not done
59 | Team Performance | You need to find out which team member improved the most since last quarter. | Go to Team Performance → Performance Data. Compare scores for this quarter vs. last quarter. Identify the biggest improvement. | Not done
60 | Team Performance | HR asks for a list of all team members currently on the platform. | Open Team Performance → Team Members List. Export or copy the full list including roles and last-activity dates. | Not done
61 | Project Portfolio | You want to see all active quality or GRC improvement projects. | Open Project Portfolio (PMP) → Projects List. Filter for active projects. Review owner, status, and due date. | Not done
62 | Project Portfolio | A project manager asks for a status update on all projects this quarter. | Open Project Portfolio. Filter for this quarter's projects. Note which are on track, at risk, or delayed. Share the summary. | Not done
63 | System Event Logs | You need to investigate who deleted a record in the system yesterday. | Open System Event Logs → Events List. Filter for yesterday's date and deletion events. Identify the user and the record affected. | Not done
64 | System Event Logs | The IT team asks for a weekly summary of platform activity. | Go to System Event Logs → Log Statistics. Review the weekly counts of logins, edits, and key actions. Export for the IT report. | Not done
65 | System Event Logs | You want to confirm that a scheduled audit ran at the expected time. | Open System Event Logs → Events List. Search for audit run events. Confirm the timestamp matches the scheduled trigger time. | Not done
66 | Table F Engine | You want to confirm Table F is correctly classifying incoming leads. | Open Table F Engine → Output / Results View. Review a sample of recent records. Confirm the category assigned matches the expected classification. | Not done
67 | Table F Engine | A new rule was added to Table F. You need to verify it is working. | Go to Table F Engine → Configuration View. Confirm the new rule appears. Then check Output / Results View to see if records are being classified by the new rule. | Not done
68 | Table F Engine | You notice some records are not being processed by Table F. | Open Table F Engine → Data Processing Check. Look for records with errors or unprocessed status. Note the issue and raise it with the Admin. | Not done
69 | Sandbox | You want to test a new scorecard without affecting live data. | Open the Sandbox environment. Run a test audit using the new scorecard. Review results and confirm they do not appear in the live Quality Dashboard. | Not done
70 | Sandbox | A new team member wants to practice using the platform before going live. | Direct them to the Sandbox. Have them run through the main screens — audit, QMS, GRC — and mark the scenario done when they complete a full practice run. | Not done
71 | Sandbox | You want to test a new automation trigger before activating it in production. | Set up the trigger in the Sandbox first. Run a test to confirm it fires correctly and produces the expected audit result. Then replicate in production. | Not done
72 | PDPL Privacy Compliance | The DPO asks for the current PDPL compliance status. | Open PDPL Privacy Compliance → Compliance Status. Review the overall status and any outstanding obligations. Share the summary with the DPO. | Not done
73 | PDPL Privacy Compliance | You need to confirm which personal data categories are being held. | Go to PDPL Privacy Compliance → Data Inventory. Review the list of data categories, their storage location, and retention period. | Not done
74 | PDPL Privacy Compliance | A new data processing activity was added. You need to record it. | Open PDPL Data Inventory. Add a new entry for the data processing activity, including purpose, data category, storage location, and responsible owner. | Not done
75 | Users & Access Control | You want to check how many active users are on the platform. | Open Users & Access Control → User Statistics. Note the total number of active users, their roles, and last login dates. | Not done
76 | Users & Access Control | A new team member needs access to the GRC module. | Go to Users & Access Control. Find the user. Assign or update their role to include GRC access. Confirm by checking their permissions. | Not done
77 | Users & Access Control | A team member has left. You need to remove their access. | Open Users & Access Control. Find the user. Deactivate or remove their account. Confirm they can no longer log in. | Not done
78 | Scorecard | You want to compare quality scores across teams for this month. | Open Scorecard → Snapshot. Filter for this month. Review scores by team and identify any team below the target threshold. | Not done
79 | Scorecard | A team leader asks for their team's scorecard trend over the last 3 months. | Go to Scorecard → Snapshot. Filter or compare across the last 3 months. Share the trend with the team leader. | Not done
80 | Scorecard | You need to confirm the scorecard is using the latest governance document version. | Open Admin Panel → Governance Documents. Note the current version. Then open Scorecard and confirm audit results reference the same version. | Not done
81 | Duplicate Radar | You want to check how many duplicate leads exist before the monthly import. | Open Duplicate Radar → Duplicate Summary. Review the current duplicate count for Leads. Flag any spikes for investigation before importing more records. | Not done
82 | Duplicate Radar | A sales manager reports that some deals appear twice in the CRM. | Open Duplicate Radar. Review the duplicate count for Deals. Drill in to identify the duplicated records and take action to merge or remove them. | Not done
83 | Duplicate Radar | You want to confirm the deduplication rules are reducing duplicates over time. | Open Duplicate Radar → Duplicate Summary. Review the trend over the last 3 months. Confirm the count is decreasing since dedup rules were applied. | Not done
84 | Quality–GRC Handoffs | A quality issue was escalated to GRC last week. You want to check its status. | Open Quality–GRC Handoffs → Handoff Summary. Filter for last week. Find the relevant handoff and check its current status and owner in GRC. | Not done
85 | Quality–GRC Handoffs | You need to confirm the rules for when quality issues automatically go to GRC. | Go to Quality–GRC Handoffs → Handoff Rules. Review the trigger conditions (e.g. score below threshold, specific issue type). Confirm they match current policy. | Not done
86 | Quality–GRC Handoffs | You want to report on how many quality issues were escalated to GRC this quarter. | Open Quality–GRC Handoffs → Handoff Summary. Filter by this quarter. Note the count and share the breakdown by issue type. | Not done
87 | KPI Tracking | You want to check whether the team is on track to meet this quarter's quality KPIs. | Open KPI Tracking → KPI Summary. Review the current performance vs. targets for each KPI. Flag any that are below target. | Not done
88 | KPI Tracking | Leadership asks which KPIs are at risk of missing their year-end target. | Go to KPI Tracking → KPI List. Review progress on each KPI. Identify those with less than 50% completion and flag them for leadership. | Not done
89 | KPI Tracking | A new KPI was approved by management. You need to add it to the tracker. | Open KPI Tracking → KPI List. Add a new KPI entry with name, target value, measurement frequency, and owner. | Not done
90 | Executive Dashboard | The CEO asks for a one-screen summary of platform health before the board meeting. | Open the Executive Dashboard. Review the top-level summaries for Quality, GRC, Risk, Compliance, and KPIs. Share the screenshot or export. | Not done
91 | Executive Dashboard | You want to verify the Executive Dashboard numbers are accurate before sharing. | Open the Executive Dashboard. Note a specific number (e.g. open risks). Then go to the Risk Register and confirm the count matches exactly. | Not done
92 | Executive Dashboard | A board member asks how quality scores have trended over the last quarter. | Open Executive Dashboard. Find the quality trend section. Review the 3-month trend and share the chart or summary. | Not done
93 | Executive Dashboard | You want to show a new executive how to get a full platform overview in one place. | Walk them through the Executive Dashboard, explaining each section: Quality summary, GRC status, Risk level, Compliance score, and KPI progress. | Not done